## JP
Tap Tap Quest: Production Schedule
|  | Year 2011 | [187 empty] | Year: 2012
|  | 4月 / APRIL | [12 empty] | 5月 / MAY | [21 empty] | 6月 / JUNE | [21 empty] | 7月 / JULY | [20 empty] | 8月 / AUGUST | [22 empty] | 9月 / SEPTEMBER | [21 empty] | 10月 / OCTOBER | [20 empty] | 11月 / NOVEMBER | [21 empty] | 12月 / DECEMBER | [21 empty] | 1月 / JANUARY | [21 empty] | 2月 / FEBRUARY | [20 empty] | 2月 / MARCH
|  | PRE-PRODUCTION | [14 empty] | GW |  | PRE-PRODUCTION | [17 empty] | PRE-PRODUCTION | [21 empty] | M1 | PRODUCTION 1 | [19 empty] | PRODUCTION 1 SV | [21 empty] | M2 | PRODUCTION 2 | [21 empty] | PRODUCTION 2 | [19 empty] | M3 | PRODUCTION 3 | [20 empty] | a | PRODUCTION 4 | [21 empty] | PRODUCTION 4 | [20 empty] | b | PRODUCTION 5 | [20 empty] | PRODUCTION 5 | [20 empty] | M
|  | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 18 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 19 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30
DIR | Jamie | PRE-PRODUCTION 18: Story Outline; PRE-PRODUCTION 25: Story Outline; PRE-PRODUCTION 9: Story Outline; PRE-PRODUCTION 16: Storyboards: Events; PRE-PRODUCTION 30: Storyboards: Rhythm Copy
|  | Tool Consultation | [7 empty] | Schedule | [14 empty] | Map Concept Art: World 1,2,3,4,5,6,7
|  | ROM Brushup | [7 empty] | Chara Design | [9 empty] | Character Design
|  | Poke Card |  |  | Poke Card | [14 empty] | Stage / Enemy / Gimmick Ideas
[20 empty] | Map Image: W 1,2,3 | [39 empty] | Rhythm Copy Camera: World 1,3,6 | [44 empty] | Rhythm Copy Camera: World 2,4,7 | [40 empty] | Rhythm Copy Camera World 5 | [21 empty] | Brush Up | [43 empty] | Brush Up / Debug
PLAN | Ohmori | PRE-PRODUCTION 18: Game Loop Plan; PRE-PRODUCTION 9: Game Loop Plan; PRE-PRODUCTION 16: Game Loop Spec / Multiplay Spec; PRE-PRODUCTION 6: <-- ( Design Lists: Monsters, Motion ,FX and Sound List by this point)
[10 empty] | Total Game Balance | [9 empty] | Total Game Balance |  |  |  |  | Enemy Rules & Idea, Mini Gimmick Rules & Idea, Spcl. Gimmicks | [14 empty] | Grey Map Tests | [19 empty] | Direction, Grey Map, | [44 empty] | Direction, Grey Map | [40 empty] | Direction, Grey Map | [21 empty] | Direction, All Grey Map Brush Up | [43 empty] | Brush Up / Debug
[20 empty] | Stage Editor Consult | [9 empty] | Stage Paper Plan: World 1,3,6: | [29 empty] | ●Stage Paper Plan: World 2,4,5,7:
| Planner 1 | PRODUCTION 1 4: Grey Map: World 1; PRODUCTION 1 SV 15: World 1: Monster / Object Brush up; PRODUCTION 2 1: Grey Map: World 2; PRODUCTION 2 17: World 2: Monster / Object Brush up; PRODUCTION 3 1: Grey Map: World 5; PRODUCTION 4 1: World 5: Monster / Object Brush up; PRODUCTION 4 26: All Stage Brush Up; PRODUCTION 5 1: Brush Up / Debug
| Planner 2 | PRODUCTION 1 4: Grey Map: World 3; PRODUCTION 1 SV 15: World 3: Monster / Object Brush up; PRODUCTION 2 1: Grey Map: World 4; PRODUCTION 2 17: World 4: Monster / Object Brush up; PRODUCTION 3 1: Secret Stages; PRODUCTION 4 1: Secret Stages: Monster / Object Brush up
| Planner 2 | PRODUCTION 1 4: Grey Map: World 6; PRODUCTION 1 SV 15: World 6: Monster / Object Brush up; PRODUCTION 2 1: Grey Map: World 7; PRODUCTION 2 17: World 7: Monster / Object Brush up; PRODUCTION 3 1: Secret Stages; PRODUCTION 4 1: Secret Stages: Monster / Object Brush up
SOUND | Adachi | PRE-PRODUCTION 16: Visual Judge Music Worlds 1, 3, 6; PRODUCTION 1 4: Visual Judge Music Worlds 2, 4, 5, 7; PRODUCTION 2 5: Rhythm Copy Music: World 1,3,6; PRODUCTION 2 17: Rhythm Copy Music: World 2,4,5,7; PRODUCTION 4 1: Event Music, Menu Music; PRODUCTION 5 1: Brush Up / Debug
|  | システム検証、外注管理のための物量算定 | [22 empty] | SE ベースシステム 試作実験 本制作前の設計 SEサラウンド効果実験 検証
[25 empty] | 外注契約業務 | [34 empty] | 外注管理、検品、指示と打ち合わせ
| Sound Outsource | PRODUCTION 1 4: Visual Judge World 1.3.6 SE制作; PRODUCTION 1 SV 2: Visual Judge World 2.4.7 SE作成; PRODUCTION 2 6: Visual Judge World5, シークレットステージ SE制作; PRODUCTION 2 29: Ryhthm Copy 1.3.6 / 2ＤMENU FX SE制作; PRODUCTION 3 15: Ryhthm Copy 2.4.7 SE MENU FX SE制作; PRODUCTION 4 19: Ryhthm Copy 5 SE作成; PRODUCTION 4 5: EVENT SE制作; PRODUCTION 4 24: 修正、調整対応
[71 empty] | Visual Judge World 1.3.6 データ入込み、調整 | [24 empty] | Visual Judge World 2.4.7データ入込み、調整 | [14 empty] | Visual Judge World5, シークレットステージ入れ込み調整 | [26 empty] | Ryhthm Copy 1.3.6 / 2ＤMENU FX SE 入れ込み、調整 | [25 empty] | Ryhthm Copy 2.4.7 SE MENU FX SEデータ入れ込み、調整 | [20 empty] | RyhthmCopy 5 データ入れ込み調整 | [11 empty] | IVENT SE データ入れ込み、調整
PROG | Sogabe | PRE-PRODUCTION 9: ベースシステム作成; PRODUCTION 1 19: ワールド２、４、７ギミック作成; PRODUCTION 2 20: リズムコピー１、３、６、作成および２Dメニュー、FX; PRODUCTION 4 12: リズムコピー５作成およびイベント
[50 empty] | ワールド１、３、６ギミック作成 | [44 empty] | ワールド５、シークレットギミック作成 | [49 empty] | リズムコピー２、４、７、作成および２Dメニュー、FXおよびイベント | [39 empty] | ブラッシュアップ、デバッグ
| Saito | PRE-PRODUCTION 9: ベースシステム作成; PRODUCTION 1 19: ワールド２、４、７ギミック作成; PRODUCTION 2 20: リズムコピー１、３、６、作成および２Dメニュー、FX; PRODUCTION 4 12: リズムコピー５作成およびイベント
[50 empty] | ワールド１、３、６ギミック作成 | [44 empty] | ワールド５、シークレットギミック作成 | [49 empty] | リズムコピー２、４、７、作成および２Dメニュー、FXおよびイベント | [39 empty] | ブラッシュアップ、デバッグ
| Watanabe | PRE-PRODUCTION 9: ツール作成およびメンテナンス
ブラッシュアップ、デバッグ
DES | Lead Designer | PRE-PRODUCTION 1: Design Tests: Map / FX Format; PRODUCTION 1 19: 2D Menu, & FX; PRODUCTION 2 1: 2D Menu, & FX; PRODUCTION 3 1: 2D Menu, & FX; PRODUCTION 4 1: 2D Menu, & FX; PRODUCTION 5 1: 2D Menu, & FX Final Brush Up
[50 empty] | Map Graphics ( half test, aim for real ) | [20 empty] | Map Supervision & Brush Up | [31 empty] | Map Supervision & Brush Up | [42 empty] | Map Supervision & Brush Up | [21 empty] | Map Supervision & Brush Up | [43 empty] | Map: Final Brush Up | [20 empty] | Debug
[71 empty] | Gimmick / Map Object Model and Motion | [31 empty] | Gimmick / Map Object Model and Motion | [42 empty] | Gimmick / Map Object Model and Motion | [21 empty] | Gimmick / Map Object Model and Motion | [43 empty] | Gimmick / Map Object Brush Up
| Chara.Model | PRE-PRODUCTION 1: Character Tests: Setup, Format; PRE-PRODUCTION 13: Hero; PRE-PRODUCTION 20: Monsters: World 1,3,6; PRODUCTION 1 19: Bosses: World 1,3,6; PRODUCTION 1 SV 22: Monsters: World 2,4,5,7; PRODUCTION 2 20: Bosses: World 2,4,5,7; PRODUCTION 3 1: Event Characters; PRODUCTION 4 10: Event Objects / General Objects; PRODUCTION 5 1: Character Model Brush Up; PRODUCTION 5 1: Debug
| Chara.Motion | PRE-PRODUCTION 20: Hero Motion; PRODUCTION 5 1: Hero Motion Brush Up; PRODUCTION 5 1: Debug
[60 empty] | Monster Motion: World 1,3,6 | [19 empty] | Boss Motion: World 1,3,6 | [22 empty] | Monster Motion: World 2,4,5,7 | [27 empty] | Boss Motion: World 2,4,5,7 | [36 empty] | Event Motion | [43 empty] | Character Motion Brush Up
Camera+ Chara.Motion
Event Camera
| Map Outsource | PRODUCTION 2 1: Map: Visual Judge: World 1, 3, 6; PRODUCTION 3 1: Map: Visual Judge: World 2, 4, 7; PRODUCTION 4 26: Map: Visual Judge: World 5, Secret Stages; PRODUCTION 5 1: Map: Visual Judge Brush Up
[103 empty] | Map: Rhythm Copy: World 1, 3, 6 | [42 empty] | Map: Rhythm Copy: World 2,4,7 | [21 empty] | & World 5 | [27 empty] | Map: Rhythm Copy Brush Up
[146 empty] | Map: Event | [49 empty] | Map: Event Brush Up

## ENG
Tap Tap Quest: Production Schedule
|  | Year 2011 | [187 empty] | Year: 2012
|  | 4月 / APRIL | [12 empty] | 5月 / MAY | [21 empty] | 6月 / JUNE | [21 empty] | 7月 / JULY | [20 empty] | 8月 / AUGUST | [22 empty] | 9月 / SEPTEMBER | [21 empty] | 10月 / OCTOBER | [20 empty] | 11月 / NOVEMBER | [21 empty] | 12月 / DECEMBER | [21 empty] | 1月 / JANUARY | [21 empty] | 2月 / FEBRUARY | [20 empty] | 2月 / MARCH
|  | PRE-PRODUCTION | [14 empty] | GW |  | PRE-PRODUCTION | [17 empty] | PRE-PRODUCTION | [21 empty] | M1 | PRODUCTION 1 | [19 empty] | PRODUCTION 1 | [21 empty] | M2 | PRODUCTION 2 | [21 empty] | PRODUCTION 2 | [19 empty] | M3 | PRODUCTION 3 | [20 empty] | a | PRODUCTION 4 | [21 empty] | PRODUCTION 4 | [20 empty] | b | PRODUCTION 5 | [20 empty] | PRODUCTION 5 | [20 empty] | M
|  | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 18 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 27 | 28 | 29 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 19 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30
DIR | Jamie | PRE-PRODUCTION 18: Story Outline; PRE-PRODUCTION 25: Story Outline; PRE-PRODUCTION 9: Story Outline; PRE-PRODUCTION 16: Storyboards: Events; PRE-PRODUCTION 30: Storyboards: Rhythm Copy
|  | Tool Consultation | [7 empty] | Schedule | [14 empty] | Map Concept Art: World 1,2,3,4,5,6,7
|  | ROM Brushup | [7 empty] | Chara Design | [9 empty] | Character Design
|  | Poke Card |  |  | Poke Card | [14 empty] | Stage / Enemy / Gimmick Ideas
[20 empty] | Map Image: W 1,2,3 | [39 empty] | Rhythm Copy Camera: World 1,3,6 | [44 empty] | Rhythm Copy Camera: World 2,4,7 | [40 empty] | Rhythm Copy Camera World 5 | [21 empty] | Brush Up | [43 empty] | Brush Up / Debug
PLAN | Ohmori | PRE-PRODUCTION 18: Game Loop Plan; PRE-PRODUCTION 9: Game Loop Plan; PRE-PRODUCTION 16: Game Loop Spec / Multiplay Spec; PRE-PRODUCTION 6: <-- ( Design Lists: Monsters, Motion ,FX and Sound List by this point)
[10 empty] | Total Game Balance | [9 empty] | Total Game Balance |  |  |  |  | Enemy Rules & Idea, Mini Gimmick Rules & Idea, Spcl. Gimmicks | [14 empty] | Grey Map Tests | [19 empty] | Direction, Grey Map, | [44 empty] | Direction, Grey Map | [40 empty] | Direction, Grey Map | [21 empty] | Direction, All Grey Map Brush Up | [43 empty] | Brush Up / Debug
[20 empty] | Stage Editor Consult | [9 empty] | Stage Paper Plan: World 1,3,6: | [29 empty] | ●Stage Paper Plan: World 2,4,5,7:
| Planner 1 | PRODUCTION 1 4: Grey Map: World 1; PRODUCTION 1 15: World 1: Monster / Object Brush up; PRODUCTION 2 1: Grey Map: World 2; PRODUCTION 2 17: World 2: Monster / Object Brush up; PRODUCTION 3 1: Grey Map: World 5; PRODUCTION 4 1: World 5: Monster / Object Brush up; PRODUCTION 4 26: All Stage Brush Up; PRODUCTION 5 1: Brush Up / Debug
| Planner 2 | PRODUCTION 1 4: Grey Map: World 3; PRODUCTION 1 15: World 3: Monster / Object Brush up; PRODUCTION 2 1: Grey Map: World 4; PRODUCTION 2 17: World 4: Monster / Object Brush up; PRODUCTION 3 1: Secret Stages; PRODUCTION 4 1: Secret Stages: Monster / Object Brush up
| Planner 2 | PRODUCTION 1 4: Grey Map: World 6; PRODUCTION 1 15: World 6: Monster / Object Brush up; PRODUCTION 2 1: Grey Map: World 7; PRODUCTION 2 17: World 7: Monster / Object Brush up; PRODUCTION 3 1: Secret Stages; PRODUCTION 4 1: Secret Stages: Monster / Object Brush up
SOUND | Adachi | PRE-PRODUCTION 16: Visual Judge Music Worlds 1, 3, 6; PRODUCTION 1 4: Visual Judge Music Worlds 2, 4, 5, 7; PRODUCTION 2 5: Rhythm Copy Music: World 1,3,6; PRODUCTION 2 17: Rhythm Copy Music: World 2,4,5,7; PRODUCTION 4 1: Event Music, Menu Music; PRODUCTION 5 1: Brush Up / Debug
|  | System verification and Amount of calculation for order | [22 empty] | SE Base System Making for trial purposes Design Effect of surround Verification
[25 empty] | Contract business | [34 empty] | Subcontract control Inspecting goods Instruction Meeting etc…
| Sound Outsource | PRODUCTION 1 4: Visual Judge World 1.3.6 SE; PRODUCTION 1 2: Visual Judge World 2.4.7 SE; PRODUCTION 2 6: Visual Judge World5, Secret Stage SE; PRODUCTION 2 29: Ryhthm Copy 1.3.6 / 2ＤMENU FX SE; PRODUCTION 3 15: Ryhthm Copy 2.4.7 SE MENU FX SE; PRODUCTION 4 19: Ryhthm Copy 5 SE; PRODUCTION 4 5: EVENT SE; PRODUCTION 4 24: Correction,Adjustment
[71 empty] | Visual Judge World 1.3.6 Making to data ,Adjustment | [24 empty] | Visual Judge World 2.4.7 Making to data ,Adjustment | [14 empty] | Visual Judge World5, Secret Stage Making to data Adjustment | [26 empty] | Ryhthm Copy 1.3.6 / 2ＤMENU FX SE Making to data Adjustment | [25 empty] | Ryhthm Copy 2.4.7 SE MENU FX SEMaking to data Adjustment | [20 empty] | RyhthmCopy 5 Making to data Adjustment | [11 empty] | EVENT SE Making to data Adjustment
PROG | Sogabe | PRE-PRODUCTION 9: BaseSystem; PRODUCTION 1 19: World２、４、７ Gimmick making; PRODUCTION 2 20: Rhythms copies 1, 3, and 6, making, 2D menus, and FX; PRODUCTION 4 12: Rhythms copies 5 making and Events
[50 empty] | World１、３、６ Gimmick making | [44 empty] | World５、Secret Gimmick making | [49 empty] | Rhythms copies 2, 4, and 7, making, 2D menus, and FX and Events | [39 empty] | Brush Up / Debug
| Saito | PRE-PRODUCTION 9: BaseSystem; PRODUCTION 1 19: World２、４、７ Gimmick making; PRODUCTION 2 20: Rhythms copies 1, 3, and 6, making, 2D menus, and FX; PRODUCTION 4 12: Rhythms copies 5 making and Events
[50 empty] | World１、３、６ Gimmick making | [44 empty] | World５、Secret Gimmick making | [49 empty] | Rhythms copies 2, 4, and 7, making, 2D menus, and FX and Events | [39 empty] | Brush Up / Debug
| Watanabe | PRE-PRODUCTION 9: Tool making and maintenance
Brush Up / Debug
DES | Lead Designer | PRE-PRODUCTION 1: Design Tests: Map / FX Format; PRODUCTION 1 19: 2D Menu, & FX; PRODUCTION 2 1: 2D Menu, & FX; PRODUCTION 3 1: 2D Menu, & FX; PRODUCTION 4 1: 2D Menu, & FX; PRODUCTION 5 1: 2D Menu, & FX Final Brush Up
[50 empty] | Map Graphics ( half test, aim for real ) | [20 empty] | Map Supervision & Brush Up | [31 empty] | Map Supervision & Brush Up | [42 empty] | Map Supervision & Brush Up | [21 empty] | Map Supervision & Brush Up | [43 empty] | Map: Final Brush Up | [20 empty] | Debug
[71 empty] | Gimmick / Map Object Model and Motion | [31 empty] | Gimmick / Map Object Model and Motion | [42 empty] | Gimmick / Map Object Model and Motion | [21 empty] | Gimmick / Map Object Model and Motion | [43 empty] | Gimmick / Map Object Brush Up
| Chara.Model | PRE-PRODUCTION 1: Character Tests: Setup, Format; PRE-PRODUCTION 13: Hero; PRE-PRODUCTION 20: Monsters: World 1,3,6; PRODUCTION 1 19: Bosses: World 1,3,6; PRODUCTION 1 22: Monsters: World 2,4,5,7; PRODUCTION 2 20: Bosses: World 2,4,5,7; PRODUCTION 3 1: Event Characters; PRODUCTION 4 10: Event Objects / General Objects; PRODUCTION 5 1: Character Model Brush Up; PRODUCTION 5 1: Debug
| Chara.Motion | PRE-PRODUCTION 20: Hero Motion; PRODUCTION 5 1: Hero Motion Brush Up; PRODUCTION 5 1: Debug
[60 empty] | Monster Motion: World 1,3,6 | [19 empty] | Boss Motion: World 1,3,6 | [22 empty] | Monster Motion: World 2,4,5,7 | [27 empty] | Boss Motion: World 2,4,5,7 | [36 empty] | Event Motion | [43 empty] | Character Motion Brush Up
Camera+ Chara.Motion
Event Camera
| Map Outsource | PRODUCTION 2 1: Map: Visual Judge: World 1, 3, 6; PRODUCTION 3 1: Map: Visual Judge: World 2, 4, 7; PRODUCTION 4 26: Map: Visual Judge: World 5, Secret Stages; PRODUCTION 5 1: Map: Visual Judge Brush Up
[103 empty] | Map: Rhythm Copy: World 1, 3, 6 | [42 empty] | Map: Rhythm Copy: World 2,4,7 | [21 empty] | & World 5 | [27 empty] | Map: Rhythm Copy Brush Up
[146 empty] | Map: Event | [49 empty] | Map: Event Brush Up